## Sheet1
NOTE: timeline is a proposed implementation of recommendations from Arts and Culture Facilities Feasibility study. Actions listed are subject to available funding and resources, reviewed on an annual basis.
|  | 15/16 |  | 16/17 |  | 17/18 |  | 18/19 |  | 19/20
| Major Recommendations | 2015 | 2016 | 2016 | 2017 | 2017 | 2018 | 2018 | 2019 | 2019 | 2020
S3. | Consider postponing demolition of facilities at PB Ronald Reserve until alternative storage facilities can be identified for user groups
1 | Adopt the Hub and Spokes model for the operation of arts and cultural facilities planning and operations
2 | Adopt the Hierarchy of Facility Provision (Regional, Municipal and Local significance outlined in this study) as a guide for the future planning and provision of arts facilities in Cardinia Shire and incorporate sites and facilities in Township, planning and structure plans
3 | Adopt a new Vision for cultural facilities planning
4 | Consider Cultural Precincts as part of the implementation and future planning of structure plans and Shire-wide planning
5 | Develop & adopt a Cultural and Community Facilities Provision Plan, similar to the Recreation Reserve Facility Standards Policy (February 2011[1])
6 | Develop brief to refurbish Cardinia Cultural Centre as a performing arts centre including a new small exhibition gallery
S10 | Review community hire costs at Cardinia Cultural Centre as part of business plan development
7 | A. Include planning for community art spaces (such as artist studios, exhibition, wet, storage and rehearsal spaces) when reviewing Township and Precinct Structure Plans and when designing new community centres, libraries and other community facilities aligned to Community Arts Centre Requirements Table in Section 8 of this report and based on Hub and Spokes model B. Amend planning of the proposed Emerald Community Hub to include facilities for community arts
8 | Officer Secondary College Community Hub Project - multi-purpose arts facility
9 | Scope potential for increasing staffing to support planning and provision of arts and cultural facilities See note on staff resourcing below and Section 3.3.6 of this Study
10 | Identify rehearsal and storage facilities for community arts groups that are located within reasonable proximity to existing arts and cultural facilities such as Cardinia Cultural Centre, the Gem Community Arts Centre and Officer Community Hub
S7 | Identify key arts and cultural organisations fulfilling a leadership role in the Shire and explore new partnerships to assist them in attracting new resources and support
S8. | A. Develop How to set up an Exhibition Space with tips and advice for local community houses, learning centres, senior centres etc. (based on the Hub & Spokes these spaces would act as spokes) B. Host a follow up workshop for interested parties with a gallery curator as guest speaker
S12. | A. Pop Up – purchase portable infrastructure (truck and/or caravan) to supplement arts and cultural facilities in smaller townships
12 | Engage with community organisations, neighbourhood houses and community centres to plan and/or upgrade three (3) community art galleries across the Shire based on the Hub & Spokes model
S13 | Establish shared administration program for arts groups through community grants program (see Section 11)
S14 | Identify a new site for Emerald Art Society for conducting classes and workshops close to the town centre. Possibly vacant shop in Emerald for workshops/classes or as part of new proposed gallery in Emerald.
S2 | Complete work on identifying all community facilities (e.g. halls) and essential data and enter all data into the Cultural Spaces Database developed by the Victorian Government and City of Melbourne
S5 | Engage with local Festivals to provide opportunities for arts events and exhibitions.
S6 | Shire wide marketing strategy to target arts and festival activity
S11 | Establish visual arts program in the proposed new gallery space at CCC
S1 | Identify council owned and community facilities that could be utilised for storage and office accommodation throughout the Shire. Explore developing an Expression of Interest process to ensure equitable access
S4 | Expand networking events for local artists and groups; five events per year based on Hub and Spokes model e.g. Pakenham, Emerald, Beaconsfield, Bunyip and Koo wee Rup (e.g. City of Kingston’s schmooze events)
S16 | Cardinia Shire to consider how to support community museums. This may include a contracted short term staff member to oversee a scoping study of local community museums undertaken in collaboration with historical societies to: • strengthen the role of collecting organisations • increase public access to significant historical objects and stories • ascertain the needs of sector in relationship to current and new facilities
11 | Undertake a feasibility study on a proposed community arts centre in Officer, Pakenham or Beaconsfield based on Hub and Spokes model.
13 | Undertake a business case analysis for the proposed Public Gallery in Emerald see Appendix 6. Note ongoing operational costs est. $200K per annum Note: this is formation of community 'trust' or 'working group' to begin raising of funds and begin business case analysis into Regional Gallery in Cardinia Shire
S15 | Develop Artist in Resident program in vacant shops, buildings, factories etc. Meet with Trader groups to identify vacant shops & buildings and Council to act as broker for artists and arts groups (see Section 11)
S9 | Refurbish Koo Wee Rup Community Centre to upgrade and modernise facilities, including lighting, exploring the provision of additional performing and exhibition facilities